## Instructions
SDLC-Test-Tracker — QAMVP Mock Trading SUT
Source Markdown: test-doc/README.md and 01–08 documents.
REQ IDs match 02-functional-requirements-specification.md; BR IDs match 01-business-requirements-document.md.
Regenerate: python test-doc/scripts/build_sdlc_tracker.py
Word exports: ./test-doc/scripts/export-docx.sh

## Gates
Phase | Gate_ID | Description | Owner | Planned_Date | Actual_Date | Status | Notes
Initiate | G-INIT | Project charter / PoC kickoff | Sponsor |  |  | Planned
Requirements | G-REQ | BRD+FRS baselined | PO |  |  | Planned
Design | G-DES | TDS+RTM approved | QA Lead |  |  | Planned
Build | G-BLD | SUT build on localhost | Dev |  |  | Planned
TestDesign | G-TD | Test plan active | QA Lead |  |  | Planned
TestExec | G-TE | Smoke+regression | QA |  |  | Planned
UAT | G-UAT | Sponsor demo | Sponsor |  |  | Planned
Release | G-REL | PoC closure | Sponsor |  |  | Planned

## Requirements
REQ_ID | REQ_Type | Title | BR_ID | BRD_Section | FRS_Section | Priority | Dev_Status | Test_Status | Last_Notes
REQ-FR-000 | FR | SPA localhost shell | BR-010 | §4 | §2 | P2 | Done | Planned
REQ-FR-001 | FR | Login fields present | BR-001 | §6 | §3.1 | P1 | Done | Planned
REQ-FR-002 | FR | Maker login | BR-001 | §6 | §3 | P1 | Done | Planned
REQ-FR-003 | FR | Checker login | BR-001 | §6 | §3 | P1 | Done | Planned
REQ-FR-004 | FR | Invalid login error | BR-001 | §7 | §3 | P1 | Done | Planned
REQ-FR-005 | FR | Route guard unauthenticated | BR-001 | §7 | §3 | P1 | Done | Planned
REQ-FR-010 | FR | Navbar persistent | BR-011 | §6 | §4.1 | P1 | Done | Planned
REQ-FR-011 | FR | User role display | BR-006 | §6 | §4.1 | P1 | Done | Planned
REQ-FR-012 | FR | Trading click menu | BR-011 | §6 | §4.1 | P1 | Done | Planned
REQ-FR-013 | FR | Admin menu users | BR-013 | §6 | §4.1 | P1 | Done | Planned
REQ-FR-014 | FR | Logout | BR-012 | §7 | §4.1 | P1 | Done | Planned
REQ-FR-020 | FR | Dashboard approved only | BR-005 | §7 | §5 | P1 | Done | Planned
REQ-FR-021 | FR | Dashboard columns | BR-005 | §7 | §5 | P1 | Done | Planned
REQ-FR-022 | FR | Total trades count | BR-005 | §7 | §5 | P1 | Done | Planned
REQ-FR-023 | FR | Dashboard loading | BR-008 | §9 | §5 | P1 | Done | Planned
REQ-FR-030 | FR | New trade fields | BR-002 | §7 | §6 | P1 | Done | Planned
REQ-FR-031 | FR | Async price total | BR-002 | §7 | §6 | P1 | Done | Planned
REQ-FR-032 | FR | GTC expiration | BR-002 | §7 | §6 | P1 | Done | Planned
REQ-FR-033 | FR | Submit trade | BR-002 | §7 | §6 | P1 | Done | Planned
REQ-FR-034 | FR | Submit toast | BR-002 | §7 | §6 | P1 | Done | Planned
REQ-FR-035 | FR | Validation | BR-002 | §6 | §6 | P2 | Done | Planned
REQ-FR-040 | FR | Queue pending filter | BR-003 | §7 | §7 | P1 | Done | Planned
REQ-FR-041 | FR | Queue columns | BR-004 | §7 | §7 | P1 | Done | Planned
REQ-FR-042 | FR | Pending count | BR-004 | §7 | §7 | P1 | Done | Planned
REQ-FR-043 | FR | Per-row approve | BR-004 | §7 | §7 | P1 | Done | Planned
REQ-FR-044 | FR | Approve toast | BR-004 | §7 | §7 | P1 | Done | Planned
REQ-FR-045 | FR | Post-approve state | BR-003 | §7 | §7 | P1 | Done | Planned
REQ-FR-050 | FR | Trade list columns | BR-005 | §6 | §8 | P2 | Done | Planned
REQ-FR-051 | FR | Trade list summary bar | BR-005 | §6 | §8 | P2 | Done | Planned
REQ-FR-060 | FR | Admin placeholder | BR-013 | §6 | §9 | P3 | Done | Planned
REQ-NFR-001 | NFR | Local operability | BR-010 | §4 | §10 | P1 | Done | Planned
REQ-NFR-002 | NFR | data-testid hooks | BR-009 | §6 | §10 | P1 | Done | Planned
REQ-NFR-003 | NFR | Responsive qualitative | BR-010 | §4 | §10 | P3 | Done | Planned
REQ-NFR-004 | NFR | Error UX | BR-008 | §9 | §10 | P2 | Done | Planned
REQ-NFR-005 | NFR | Performance PoC | BR-008 | §9 | §10 | P3 | Done | Planned
REQ-SEC-001 | SEC | Role labeling | BR-006 | §8 | §11 | P1 | Done | Planned
REQ-SEC-002 | SEC | Session termination | BR-012 | §7 | §11 | P1 | Done | Planned
REQ-SEC-003 | SEC | Pedagogical limitation doc | BR-007 | §8 | §11 | P2 | Done | Planned

## Tickets
TKT_ID | Theme | REQ_IDs | Sprint | Dev_Owner | QA_Owner | Status | BRD_Ref | FRS_Ref
TKT-QAMVP-000 | System shell | REQ-FR-000 | S1 | Dev | QA | Open | BRD §4 | FRS §2
TKT-QAMVP-101 | Auth happy | REQ-FR-001,002,003 | S1 | Dev | QA | Open | BRD §6 | FRS §3
TKT-QAMVP-102 | Auth negative | REQ-FR-004,005 | S1 | Dev | QA | Open | BRD §7 | FRS §3
TKT-QAMVP-110 | Navigation | REQ-FR-010,011,012 | S1 | Dev | QA | Open | BRD §6 | FRS §4
TKT-QAMVP-111 | Admin nav | REQ-FR-013 | S1 | Dev | QA | Open | BRD §6 | FRS §4
TKT-QAMVP-112 | Logout | REQ-FR-014 | S1 | Dev | QA | Open | BRD §7 | FRS §4
TKT-QAMVP-120 | Dashboard | REQ-FR-020,021,022,023 | S2 | Dev | QA | Open | BRD §7 | FRS §5
TKT-QAMVP-130 | Trade form A | REQ-FR-030,031,032 | S2 | Dev | QA | Open | BRD §7 | FRS §6
TKT-QAMVP-131 | Trade submit | REQ-FR-033,034 | S2 | Dev | QA | Open | BRD §7 | FRS §6
TKT-QAMVP-132 | Trade validation | REQ-FR-035 | S2 | Dev | QA | Open | BRD §6 | FRS §6
TKT-QAMVP-140 | Queue view | REQ-FR-040,041,042 | S2 | Dev | QA | Open | BRD §7 | FRS §7
TKT-QAMVP-141 | Queue approve | REQ-FR-043,044,045 | S2 | Dev | QA | Open | BRD §7 | FRS §7
TKT-QAMVP-150 | Trade list | REQ-FR-050,051 | S3 | Dev | QA | Open | BRD §6 | FRS §8
TKT-QAMVP-160 | Admin page | REQ-FR-060 | S3 | Dev | QA | Open | BRD §6 | FRS §9
TKT-QAMVP-201 | NFR core | REQ-NFR-001,002 | S3 | Dev | QA | Open | BRD §4 | FRS §10
TKT-QAMVP-202 | NFR UX | REQ-NFR-003,004 | S3 | Dev | QA | Open | BRD §4 | FRS §10
TKT-QAMVP-203 | NFR perf | REQ-NFR-005 | S3 | Dev | QA | Open | BRD §9 | FRS §10
TKT-QAMVP-301 | SEC session | REQ-SEC-001,002 | S3 | Dev | QA | Open | BRD §8 | FRS §11
TKT-QAMVP-302 | SEC docs | REQ-SEC-003 | S3 | QA | QA | Open | BRD §8 | FRS §11

## TestExecution
TC_ID | REQ_ID | TKT_ID | BRD_Section | FRS_Section | TDS_Ref | Suite | Environment | Last_Run | Result | Defect_ID | Automation_Path
TC-AUTH-001 | REQ-FR-001 | TKT-QAMVP-101 | BRD §6 | FRS §3.1 | TD-REQ-FR-001 | S-1 | ENV-LOCAL-01 |  | Planned |  | test_data/generated-scripts/
TC-AUTH-002 | REQ-FR-002 | TKT-QAMVP-101 | BRD §6 | FRS §3 | TD-REQ-FR-002 | S-1 | ENV-LOCAL-01 |  | Planned
TC-AUTH-003 | REQ-FR-003 | TKT-QAMVP-101 | BRD §6 | FRS §3 | TD-REQ-FR-003 | S-1 | ENV-LOCAL-01 |  | Planned
TC-AUTH-004 | REQ-FR-004 | TKT-QAMVP-102 | BRD §7 | FRS §3 | TD-REQ-FR-004 | S-3 | ENV-LOCAL-01 |  | Planned
TC-AUTH-005 | REQ-FR-005 | TKT-QAMVP-102 | BRD §7 | FRS §3 | TD-REQ-FR-005 | S-3 | ENV-LOCAL-01 |  | Planned
TC-NAV-003 | REQ-FR-012 | TKT-QAMVP-110 | BRD §6 | FRS §4.1 | TD-REQ-FR-012 | S-2 | ENV-LOCAL-01 |  | Planned
TC-TRADE-004 | REQ-FR-033 | TKT-QAMVP-131 | BRD §7 | FRS §6 | TD-REQ-FR-033 | S-1 | ENV-LOCAL-01 |  | Planned
TC-QUEUE-004 | REQ-FR-043 | TKT-QAMVP-141 | BRD §7 | FRS §7 | TD-REQ-FR-043 | S-1 | ENV-LOCAL-01 |  | Planned
TC-DASH-001 | REQ-FR-020 | TKT-QAMVP-120 | BRD §7 | FRS §5 | TD-REQ-FR-020 | S-1 | ENV-LOCAL-01 |  | Planned

## Defects
Defect_ID | Sev | Summary | REQ_ID | TKT_ID | Status | Opened | Closed
(none yet)

## SignOff
Gate | Role | Name | Date | Approved_Y_N | Comment
G-TD | QA Lead
G-TE | QA Lead
G-UAT | Sponsor